Planning and design a coding project

Planning and designing a coding project ​involves:
1. Defining project requirements
2. Setting objectives
3. Creating ​a design outline that includes key coding concepts

Let's explore these steps using an example. ​You want to build a task management app to ​help your co-workers keep track of their tasks. ​First, begin by defining project requirements.

Defining project requirements

​Recall that a project's requirements ​are the outcomes that must be met and ​the tasks that must be ​completed to ensure its success and completion on time.

​Project requirements come in ​two main categories, functional and non-functional. ​

Functional requirements define what the app needs to do, ​the essential functions that make the app work. ​They answer questions like, what ​should the app accomplish? ​The functional requirements for ​our task management app are straightforward. ​The app must allow users to add, ​review, and complete tasks. ​These are the basic actions that make the app useful.

​Non-functional requirements ​cover how the app should perform. ​These are aspects like usability, ​performance, and security. ​They ensure the app is not just functional, ​but also reliable and enjoyable to use. ​The non-functional requirements for ​the task app focus on usability and performance. ​The app should have an interface that's ​intuitive and that allows users to create, ​edit, and delete ​tasks with no more than three selections. ​The app also should be able to load ​the task list within two seconds and be ​able to handle up to 10,000 ​tasks without performance degradation.

Setting project objectives

With our requirements in place, ​the next step is to set clear project objectives.
​Recall that objectives are specific results that ​a person or process aims to achieve within a time frame. ​For our app, these might include:
1. Building the code base ​for adding and reviewing and completing ​tasks within three months
2. Implementing data integration for ​task storage within four months
3. Completing testing and debugging, ​resolving 95 percent of critical bugs before the release.
These objectives are measurable. ​We can always check if the app ​is meeting them as we build. ​Clear objectives provide direction ​and help maintain project timelines. ​They ensure everyone involved knows ​exactly what needs to be accomplished. ​With well-defined objectives, ​we can allocate resources like time, ​effort, and budget more effectively, ​making the entire process smoother.

Design outline

Now let's move on to creating a design outline. ​This is where we transform our requirements and ​objectives into a plan for how the app will function. ​A design outline acts as ​a step by step guide for building the app. ​To design our task management app:

1. We'll break the project into ​smaller and manageable modules. ​For our task app, we need:
  1.1 Module for viewing tasks that will provide ​a simple interface for users ​to review their task list any time
  1.2 We also need a module for adding tasks. ​This module focuses on ​a straightforward way to input new tasks.
  1.3 Finally, we need a module for marking tasks as complete. ​This module will provide checkbox ​interface elements that can be selected. ​
2. Plan coding components we will use to implement them. ​To implement the modules, ​we need to use variables, ​methods, if/else statements, and loops. ​Since variable store information, first, ​we should outline where we will need ​to keep data throughout the project. ​For example, in our to do list app, ​we need a string variable for each task. Each time the user adds a task, ​it is stored in an array or a list of variables. ​Next, we should design the methods. ​These will enable us to group related tasks ​into one reusable unit of code. ​In the to-do list app, ​we should have a method for each module, ​including view task, add task, ​and mark task complete. ​Next, we'll plan out where ​the decisions in our app happen. ​We'll use if/else statements to handle ​different scenarios based on conditions. ​For instance, we'll plan to use ​an if/else statement to check if ​the user has entered a task. If the input field is empty, ​we'll display a message asking the user to enter a task. ​Otherwise, we'll display a message ​to add the task to the list. ​Finally, we must determine if any of ​our modules must repeat code based on conditions. ​We'll identify where it's essential to repeat ​actions and plan to use loops to handle those situations. ​In the to-do list app, ​we'll use a loop to display all the added tasks, ​showing them on the screen each ​time the user opens the app.